## Effort Estimation
Module | Features to Test | Complexity | Est. Test Cases | Avg. Effort per TC (hrs) | Total Effort (hrs)
Login | Valid/Invalid login, session mgmt | Low | 6 | 0.5 | 3
PIM (Employee Mgmt) | Add/Edit/Delete/View employee | High | 20 | 0.75 | 15
Leave | Apply/Approve/Reject leave, history | Medium | 12 | 0.75 | 9
Time | Timesheet entry, approval | Medium | 10 | 0.75 | 7.5
Recruitment | Post job, apply, candidate mgmt | High | 15 | 1 | 15
Dashboard | Widgets, reports visibility | Low | 6 | 0.5 | 3
Total |  |  | 69 |  | 52.5

## Test Plan (Scenarios)
Module | Test Scenario Example | Priority | Test Type
Login | Verify valid login with Admin credentials | High | Functional
Login | Verify lockout after 5 invalid attempts | High | Security
PIM | Verify employee creation with mandatory fields | High | Functional
PIM | Verify upload of employee documents | Medium | Functional/Upload
Leave | Verify leave request submission by employee | High | Functional
Leave | Verify approval workflow by Admin | High | Functional
Time | Verify employee submits timesheet for a week | Medium | Functional
Time | Verify manager approves timesheet | Medium | Functional
Recruitment | Verify job vacancy creation | High | Functional
Recruitment | Verify candidate shortlisting | High | Functional
Dashboard | Verify Admin dashboard shows pending approvals | Medium | Functional/UI
Dashboard | Verify employee dashboard shows leave balance | Medium | Functional/UI

## Coverage by Roles
Module | Admin Coverage Example | ESS Coverage Example
Login | Admin login/logout | Employee login/logout
PIM | Add/Edit/Delete employee | View own profile only
Leave | Approve/Reject leave requests | Apply for leave, check status
Time | Approve employee timesheets | Submit own timesheet
Recruitment | Create vacancy, shortlist candidates | Apply for job
Dashboard | View system-wide reports and stats | View personal info, leave status

## Risk Analysis
Risk ID | Risk Description | Impact | Probability | Mitigation Plan
R1 | Login module failure due to invalid session handling | High | Medium | Perform regression on login after each release
R2 | Data loss while creating employee in PIM | High | Low | Ensure DB backup & validation testing
R3 | Leave approval workflow breaks after updates | Medium | Medium | Regression testing on workflows
R4 | Performance issues with Time/Timesheets | Medium | High | Include performance & load testing
R5 | Recruitment module errors in candidate uploads | High | Medium | Perform file validation testing

## Entry & Exit Criteria
Stage | Entry Criteria | Exit Criteria
Test Planning | Requirements finalized, test scope defined | Test plan reviewed & approved
Test Design | Test scenarios & cases identified | Peer-reviewed & signed off
Test Execution | Test environment ready, test data prepared | All planned test cases executed
Defect Management | Defect logging process in place | All critical defects closed or deferred
Test Closure | Test summary report created | Sign-off from stakeholders

## Test Summary Report
Metric | Description | Value
Total Test Cases | Total number of designed test cases | 69
Executed Test Cases | Number of executed test cases | 50
Passed | Number of passed test cases | 45
Failed | Number of failed test cases | 5
Defect Density | Defects per module tested | 0.1
Test Coverage | Executed vs Planned (%) | 72.4638